## Sheet1
Date | Task | Contributor(s) | Hours Spent
2018-01-24 | Create database table creation scripts | Kolby | 2
2018-02-07 | Read into SQL Server database connection through JDBC | Kolby | 3
2018-02-07 | Created test map and login activities | Josh | 2
2018-02-10 | Created initial LokkaL login app | Josh | 1
2018-02-11 | Work on implementing correct connection information from server to app | Kolby | 5
2018-02-18 | Debug issues with connecting app to server | Kolby | 5
2018-02-28 | Meet with Ward to get help or see about other solutions | Kolby | 1
2018-03-03 | Updated LokkaL app to include basic MapsActivity | Josh | 1
2018-03-04 | Learn how to implement REST Services | Kolby | 4
2018-03-11 | Minor UI changes and created app logos | Josh | 1
2018-03-21 | Meet with Ward to fix issues of inserting data into database | Kolby | 1
2018-03-24 | Added registration dialog box to LokkaL | Kolby | 2.5
2018-03-24 | Updated database creation scripts | Kolby | 1
2018-04-02 | Added Navigation Drawer to LokkaL | Josh | 2
2018-04-02 | Added account registration functionality and login verifcation foundation | Kolby | 1
2018-04-05 | Meet with Ward to qet quering information working with the database | Kolby | 1
2018-04-07 | Cleaned login code and updated account queries | Kolby | 1
2018-04-07 | Updated navigation drawer items and included placeholders | Josh | 3
2018-04-07 | Added new PHP and HTML files | Josh/Kolby | 3
2018-04-11 | Finalized login functionality | Kolby | 1
2018-04-14 | Minor UI navigation changes + passes person object when switching activites | Josh | 1
2018-04-14 | Added methods for connection to databse for friend requests | Kolby | 2
2018-04-14 | Created friend requests fragment and adapter | Josh | 1
2018-04-14 | Finalized sending requests | Josh/Kolby | 4
2018-04-14 | Created fragments and adapter for veiwing friend requests in RecyclerView | Josh/Kolby | 1
2018-04-14 | Added swipe functionality for accepting/rejecting requests | Kolby | 1
2018-04-14 | Created fragment and added to view friends list | Josh | 0.5
2018-04-14 | Populated friends list recycler view from database query | Kolby | 0.5
2018-04-16 | Finalized friends functionality | Josh/Kolby | 1
2018-04-16 | Minor UI changes to drawers and changed app icons | Josh | 1
2018-04-16 | Added settings functionality for changing update interval | Josh | 2
2018-04-16 | Added swipe functionality to delete current friends | Kolby | 1
2018-04-17 | Changed app colors and logo | Josh | 1
2018-04-18 | Added group and group request fragments + associated fragments | Josh | 0.5
2018-04-20 | Worked on getting group requests working | Josh/Kolby | 4
2018-04-22 | Fixed back button functionality between fragments and activities | Josh | 1
2018-04-22 | Added sign out functionality | Josh | 0.5
2018-04-22 | Removed the auto-focus on login edittexts | Josh | 0.5
2018-04-22 | Functionality to create groups, send requests and view requests | Kolby | 2.5
2018-04-22 | Finalized working group navigation functionality | Josh/Kolby | 2
2018-04-23 | Gave unique colors to markers within group | Josh | 0.5
2018-04-24 | Added group management fragment | Kolby | 1.5
2018-04-24 | Worked on presenation poster | Josh/Kolby | 2.5
2018-04-25 | Queried group members into group management fragment | Kolby | 1
2018-04-25 | Added battery life to group management list and markers | Kolby | 1.5
2018-04-26 | Final app polishing | Josh/Kolby | 1
2018-04-26 | Prepared for final presentation | Josh/Kolby | 4.5